## darrell demakes - vidstream tel
Darrell DeMakes - VidStream Telemetry Dashboard
WEEK 1 OF 12 - 14 - 3/30 - 4/2
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
Project kickoff & repo init |  | Integrate Rubric into Plan |  | 2026-03-30 | 2 | Darrell DeMakes | 11484331972
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| Review Items to add from rubrik |  |  |  | 11628376704
Scaffold backend skeleton |  | Finalize scope, create GitHub repo, decide minimal MVP and LLM provider (OpenAI vs HF). Create Express project, basic routes, linting, and package.json. Add .env example. |  | 2026-03-31 | 2 | Darrell DeMakes | 11484329167
Scaffold frontend skeleton |  | Create React (Vite/CRA) app, basic pages (Dashboard, Chat), link to backend base URL. |  | 2026-04-01 | 2 | Darrell DeMakes | 11484353713
Subitems | Name | Owner | Status | Date | Item ID (auto generated)
| JS P1-1 & P2-1: Single JS entry point — all JS in one file (app.js / main.jsx) |  |  |  | 11631442795
| JS P1-2: Link JS file to ≥1 webpage (React root or HTML page) |  |  |  | 11631463459
| JS P1-3: Use descriptive variable names throughout (e.g. rebufferRate, chartData) |  |  |  | 11631460521
| JS P1-4: Declare ≥2 variables of different types including an int (e.g. let pageCount = 0) |  |  |  | 11631463270
Local dev environment & Docker |  | Add Dockerfile(s), docker-compose stub for backend + Mongo + Chroma placeholder; document local start steps. |  | 2026-04-02 | 2 | Darrell DeMakes | 11484329168
2026-03-30 to 2026-04-02
WEEK 2 OF 12 - 15 - 4/6 - 4/9
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
Set up MongoDB Atlas |  | Create free-tier cluster, create DB and collections, connect backend and verify CRUD. |  | 2026-04-09 | 2 | Darrell DeMakes | 11484330178
Create sample runbooks & logs |  | Author 3-5 synthetic runbooks and a few redacted sample logs to be used for RAG testing. |  | 2026-04-08 | 2 | Darrell DeMakes | 11484335255
Define KPI & telemetry schemas |  | Write telemetry event schema and KPI snapshot schema (startup, rebuffer, p95, error counts). |  | 2026-04-06 | 2 | Darrell DeMakes | 11484329090
Define agent output acceptance criteria |  | Write acceptance criteria templates for post-mortem, OpenAPI skeleton, and GitHub issue outputs. |  | 2026-04-07 | 2 | Darrell DeMakes | 11484313554
2026-04-06 to 2026-04-09
WEEK 3 OF 12 - 16 - 4/13 - 4/16
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
Design KPI aggregator |  | Write design and pseudocode for KPI aggregator worker (cron), compute median & p95 logic. |  | 2026-04-13 | 2 | Darrell DeMakes | 11484332125
Implement basic aggregator |  | Implement aggregator worker that reads raw events and writes KPI snapshots to Mongo. |  | 2026-04-14 | 2 | Darrell DeMakes | 11484354262
KPI REST endpoints |  | Create endpoints to return KPI snapshots and time ranges for frontend consumption. |  | 2026-04-15 | 2 | Darrell DeMakes | 11484318004
Dashboard skeleton & data wiring |  | Create React components for KPI charts; connect to KPI endpoints (mock data if needed). |  | 2026-04-16 | 2 | Darrell DeMakes | 11484346944
2026-04-13 to 2026-04-16
WEEK 4 OF 12 - 17 - 4/20 - 4/23
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
Implement ingestion endpoint |  | Finish ingestion POST /telemetry endpoint; validate payloads and persist to raw events collection. |  | 2026-04-20 | 2 | Darrell DeMakes | 11484336037
Simulate event ingestion |  | Run telemetry simulator script to POST sample events and confirm storage and aggregator picks them up. |  | 2026-04-21 | 2 | Darrell DeMakes | 11484354129
Sprint demo & documentation |  | Prepare short demo notes, update README for sprint 1, capture risks and next sprint plan. |  | 2026-04-23 | 2 | Darrell DeMakes | 11484347718
Dashboard integration |  | Hook dashboard charts to live KPI endpoints and show basic metrics (median, p95, error rate). |  | 2026-04-22 | 2 | Darrell DeMakes | 11484314628
2026-04-20 to 2026-04-23
WEEK 5 OF 12 - 18 - 4/27 - 4/30
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
Implement scheduled aggregator (cron) |  | Configure aggregator to run on schedule (node-cron), persist KPI snapshots, add basic logging. |  | 2026-04-28 | 2 | Darrell DeMakes | 11484330096
Thresholds & simple alert rules |  | Add alert rules logic to aggregator (e.g., p95 > X, rebuffer > Y) and simple alert endpoints. |  | 2026-04-29 | 2 | Darrell DeMakes | 11484318107
Implement anomaly checker |  | Create anomaly checker that evaluates KPI snapshots and flags threshold breaches. |  | 2026-04-30 | 2 | Darrell DeMakes | 11484336040
Build telemetry simulator |  | Create a configurable Node script to simulate client events with controllable rates and error injection. |  | 2026-04-27 | 2 | Darrell DeMakes | 11484347987
2026-04-27 to 2026-04-30
WEEK 6 OF 12 - 19 - 5/4 - 5/7
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
Install & run Chroma locally |  | Install Chroma locally or container, confirm connectivity, add storage folder and docs index plan. |  | 2026-05-04 | 2 | Darrell DeMakes | 11484342225
Prepare embeddings pipeline |  | Wire embeddings call (OpenAI or HF) and create script to embed runbook/docs into Chroma. |  | 2026-05-05 | 2 | Darrell DeMakes | 11484359679
Index sample docs & logs |  | Index the synthetic runbooks and redacted logs into Chroma; verify retrieval by keyword. |  | 2026-05-06 | 2 | Darrell DeMakes | 11484339974
Retrieval API |  | Create /retrieve endpoint that returns top-K context passages from Chroma for a query. |  | 2026-05-07 | 2 | Darrell DeMakes | 11484344851
2026-05-04 to 2026-05-07
WEEK 7 OF 12 - 20 - 5/11 - 5/14
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
Integrate LangChain JS |  | Install LangChain JS; scaffold agent controller that can accept prompts and call an LLM with context. |  | 2026-05-11 | 2 | Darrell DeMakes | 11484340891
Write prompt templates |  | Write and store prompt templates for anomaly summary, post-mortem, OpenAPI, and issue generation. |  | 2026-05-12 | 2 | Darrell DeMakes | 11484322411
Test basic agent outputs |  | Run sample prompts for anomaly summary and check outputs for coherence and factual referencing. |  | 2026-05-14 | 2 | Darrell DeMakes | 11484341149
Connect retrieval to agent |  | Make agent controller call retrieval API to fetch context and include it in LLM prompts. |  | 2026-05-13 | 2 | Darrell DeMakes | 11484346138
2026-05-11 to 2026-05-14
WEEK 8 OF 12 - 21 - 5/18 - 5/21
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
Implement post-mortem generator |  | Build an endpoint that takes timeline/logs and returns a formatted post-mortem draft. Add tests. |  | 2026-05-18 | 2 | Darrell DeMakes | 11484340216
Implement GitHub issue generator |  | Create generator that forms title, description, acceptance criteria and JSON payload for GitHub issues. |  | 2026-05-19 | 2 | Darrell DeMakes | 11484322176
Implement OpenAPI skeleton generator |  | Create module to produce OpenAPI YAML/JSON from natural-language requirement inputs. |  | 2026-05-20 | 2 | Darrell DeMakes | 11484342445
Validate generated OpenAPI |  | Load generated OpenAPI into Swagger UI locally and fix schema/format issues. |  | 2026-05-21 | 2 | Darrell DeMakes | 11484342447
2026-05-18 to 2026-05-21
WEEK 9 OF 12 - 22 - 5/25 - 5/28
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
Hook anomaly checker -> agent |  | Wire anomaly checker to enqueue jobs and verify agent receives context and produces an output. |  | 2026-05-26 | 2 | Darrell DeMakes | 11484361267
Implement LLM call throttling & caching |  | Add simple caching for agent responses and throttle LLM calls to control costs. |  | 2026-05-27 | 2 | Darrell DeMakes | 11484346424
Agent job queue |  | Implement simple job queue (in-process or Redis/BullMQ) to process agent jobs enqueued by anomaly checker. |  | 2026-05-25 | 2 | Darrell DeMakes | 11484345334
Add GitHub integration stub |  | Add ability to POST generated issue payloads to GitHub (use token or env var), or simulate via local file. |  | 2026-05-28 | 2 | Darrell DeMakes | 11484342062
2026-05-25 to 2026-05-28
WEEK 10 OF 12 - 23 - 6/1 - 6/4
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
End-to-end simulated incidents (round 1) |  | Run two simulated incidents: verify dashboard alert -> agent output -> human review -> issue creation. |  | 2026-06-01 | 2 | Darrell DeMakes | 11484322378
Unit & integration tests |  | Write unit tests for aggregator, retrieval, and generators; run tests and fix failing cases. |  | 2026-06-03 | 2 | Darrell DeMakes | 11484346027
Bug fixes & stabilization |  | Fix issues surfaced by testing; improve input validation and error handling. |  | 2026-06-04 | 2 | Darrell DeMakes | 11484326589
Create Postman collection & API docs |  | Export API endpoints (ingest, KPI, retrieve, agent) as Postman collection and update README. |  | 2026-06-02 | 2 | Darrell DeMakes | 11484341882
2026-06-01 to 2026-06-04
WEEK 11 OF 12 - 24 - 6/8 - 6/11
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
Dockerize & CI prep |  | Add Dockerfiles, docker-compose for local stack, and basic CI (GitHub Actions) to run tests. |  | 2026-06-08 | 2 | Darrell DeMakes | 11484345016
Deploy frontend (Vercel) |  | Configure and deploy React frontend to Vercel; update environment variables and verify build. |  | 2026-06-09 | 2 | Darrell DeMakes | 11484322166
Deploy backend (Render/Vercel) |  | Deploy Express backend; configure Mongo Atlas connection and Chroma (if using hosted). |  | 2026-06-10 | 2 | Darrell DeMakes | 11484359798
Smoke tests on deployed app |  | Run end-to-end smoke tests against deployed endpoints and dashboard; record issues. |  | 2026-06-11 | 2 | Darrell DeMakes | 11484342036
2026-06-08 to 2026-06-11
WEEK 12 OF 12 - 25 - 6/15 - 6/18
Name | Subitems | Description | Status | Date | Duration (Days) | Person | Item ID (auto generated)
UI polish & UX tweaks |  | Polish dashboard visuals, chat UI, add tooltips and copy, and resolve UX issues from smoke tests. |  | 2026-06-15 | 2 | Darrell DeMakes | 11484328233
Documentation & README finalization |  | Write README, architecture diagram, runbook templates, and developer setup instructions. |  | 2026-06-16 | 2 | Darrell DeMakes | 11484328704
Final deliverables & interview prep |  | Package GitHub repo link, Postman/OpenAPI artifacts, demo link, one-page impact summary and resume bullets. |  | 2026-06-18 | 2 | Darrell DeMakes | 11484346054
Demo video recording & edit |  | Record 5–7 minute walkthrough demo, edit video, and upload (YouTube/drive) for sharing. |  | 2026-06-17 | 2 | Darrell DeMakes | 11484340774
2026-06-15 to 2026-06-18

## updates
Darrell DeMakes - VidStream Telemetry Dashboard | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
11484331972 | Project kickoff & repo init | Update |  | Darrell DeMakes | 11/March/2026 07:32:40 PM | Finalize scope, create GitHub repo, decide minimal MVP and LLM provider (OpenAI vs HF). | 0 |  | 5001760691